## April
| 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-05 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02
Tasks | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45
Project Wiki Creation - Developer Confluence page
Approval for resources from Boston
Approval for resources - Avant Port (AVP)
Approval for resources - Riga
MSA, SOW for Avant Port
Harvest Time accounting
VPN, JIRA, SVN, Confluence access - Riga (1 resource)
VPN, JIRA, SVN, Confluence access - Boston (2 resources)
VPN, JIRA, SVN, Confluence access - AVP (2 resources)
VPN, JIRA, SVN, Confluence access - AVP (2 resources)
TMS 8.2 licenses for Boston team
TMS 8.2 licenses for Riga team
TMS 8.2 licenses for AVP team
Ingestate architecture review
Phase I - basic alarm and alert functionality
Sprint 1 -PC client for Agent/Git-SVN, Bamboo plan
Sprint 2 - Alert and Agent research
Sprint 3 - Create design document
Sprint 4 - Create skeleton, Finish design document
Sprint 5 - Agent (Heartbeat - basic), Term/Dash communication
Sprint 6 - Alarm Configuration, Message Authentication
Sprint 7 - Create schema, save alarm configuration
Sprint 8 - Generate Alerts
Sprint 9 -Generate Alerts (cont), Basic Alert configuration, MMI UI, Desktop UI
Sprint 10 - Integration for IngEstate
Sprint Planning for Advanced congifuration and Application statistics - Phase II
Phase II - Alert notification and application events (tentative schedule)
Sprint 11 - Alert notification - e-mail/SMS
Sprint 12 - Alert notification - e-mail/SMS (continued)
Sprint 13 - Application Events and reporting (TBD)
Sprint 14 - Application Events and reporting (Continued) (TBD)
Sprint 15 - TBD